## OMS Backlog
Order Management System Sprint Planning Document
Backlog | Customer Service | Story points | Priority
1 | Search the customer based out of customer Id /name | 1
2 | Add a customer to the repository | 3
3 | Viewing a customer based out of customer Id | 2
4 | Modify the customer details based out of customerId | 3
5 | Delete a customer based out of customerId | 2
6 | Display all the customers | 1
7 | Display all the orders based out of customerId | 1
Backlog | Order Service
8 | Search an order based out of orderId | 1
9 | Create an Order with list of product items | 3
10 | Delete Order based out of orderId | 2
11 | Get the orders based out of customerId | 1
12 | Get the order based out of customer Id and OrderId | 1
Backlog | ProductCatalog Service
14 | Add a product into the repository | 3
15 | Remove a product into the respository | 2
16 | View the product existence inside the repository | 1
17 | Search a product based out of productId from the repository | 2
18 | Search a product based out of name from the repository | 2
19 | Update the product information in the repository. | 2
Backlog | Inventory Service
20 | Add the product count,threshold to inventory by using productId | 2
21 | Delete the product details to inventory by using productId | 2
22 | Update product details to inventory by using productId | 2
23 | Search the product count for a productId | 2
Backlog | Mail Service
24 | Send a confirmation mail after the order is placed | 2
25 | Send an Invoice mail if the customer requests for the specific order | 2
Backlog | Cross Cutting Concerns
26 | Implement API gateway for all the endpoints | 5
27 | Inject security for all the endpoints | 5
28 | Enable Swagger for all the endpoints. | 3
29 | Logging specific to OMS system | 3
Backlog | BillingService
30 | Create an Invoice entry for every placed order | 2
31 | Send mail to the Customer | 2
Backlog | EventService
32 | Create an event for every order creation, order status updation | 5
33 | Fetch the events based out of orderId | 3
34 | Fetch all the events based out of statuses | 3
35 | Fetch all the events based out of eventName | 3
Backlog | Others
36 | Configuring the Pivotal Environment(like configuring RabbitMQs etc) | 5
37 | Configuring the Jenkins | 5
38 | MongoDB table design | 3
39 | Design document preparation | 3
40 | Enabling Splunk | 5
Backlog | Master Data
41 | Master Data Preparation | 2
Backlog | API Test
42 | API Test Case Creation - Customer Service | 3
43 | API Test Case Creation - Order Service | 3
44 | API Test Case Creation - Inventory Service | 3
45 | API Test Case Creation - Mail Service | 3
46 | API Test Case Creation - BillingService | 3
47 | API Test Case Creation - EventService | 3

## Sprint 1
Customer Service | Story points | Owner
Search the customer based out of customer Id /name | 1 | Panneer/Ashok
Add a customer to the repository | 3 | Panneer/Ashok
Viewing a customer based out of customer Id | 2 | Panneer/Ashok
Modify the customer details based out of customerId | 3 | Panneer/Ashok
Delete a customer based out of customerId | 2 | Panneer/Ashok
Display all the customers | 1 | Panneer/Ashok
Display all the orders based out of customerId | 1 | Panneer/Ashok
ProductCatalog Service
Add a product into the repository | 3 | Michael/Ganesh
Remove a product into the respository | 2 | Michael/Ganesh
View the product existence inside the repository | 1 | Michael/Ganesh
Search a product based out of productId from the repository | 2 | Michael/Ganesh
Search a product based out of name from the repository | 2 | Michael/Ganesh
Update the product information in the repository. | 2 | Michael/Ganesh
Inventory Service
Add the product count,threshold to inventory by using productId | 2 | Rajsekar
Delete the product details to inventory by using productId | 2 | Rajsekar
Update product details to inventory by using productId | 2 | Rajsekar
Search the product count for a productId | 2 | Rajsekar
Master Data
Master Data Preparation | 2 | Jagadeesan/Sathish