## OMS Backlog
Order Management System Sprint Planning Document
Backlog | Customer Service | Story points | Priority
1 | Search the customer based out of customer Id /name | 3
2 | Add a customer to the repository | 3
3 | Viewing a customer based out of customer Id | 2
4 | Modify the customer details based out of customerId | 3
5 | Delete a customer based out of customerId | 2
6 | Display all the customers | 1
7 | Display all the orders based out of customerId | 1
Backlog | Order Service
8 | Search an order based out of orderId | 1
9 | Create an Order with list of product items | 3
10 | Delete Order based out of orderId | 2
11 | Get the orders based out of customerId | 1
12 | Get the order based out of customer Id and OrderId | 1
Backlog | Product Service
14 | Add a product into the repository | 3
15 | Remove a product into the respository | 2
16 | View the product existence inside the repository | 1
17 | Search a product based out of productId from the repository | 2
18 | Search a product based out of name from the repository | 2
19 | Update the product information in the repository. | 2
Backlog | Inventory Service
20 | Add the product count,threshold to inventory by using productId | 2
21 | Delete the product details to inventory by using productId | 2
22 | Update product details to inventory by using productId | 2
23 | Search the product count for a productId | 2
Backlog | Mail Service
24 | Send a confirmation mail after the order is placed | 2
25 | Send an Invoice mail if the customer requests for the specific order | 2
Backlog | Cross Cutting Concerns
26 | Implement API gateway for all the endpoints | 3
27 | Inject security for all the endpoints | 5
28 | Enable Swagger for all the endpoints. | 3
29 | Logging specific to OMS system | 3
Backlog | BillingService
30 | Create an Invoice entry for every placed order | 2
31 | Send mail to the Customer | 2
Backlog | EventService
32 | Create an event for every order creation, order status updation | 5
33 | Fetch the events based out of orderId | 3
34 | Fetch all the events based out of statuses | 3
35 | Fetch all the events based out of eventName | 3
Backlog | Others
36 | Configuring the Pivotal Environment(like configuring RabbitMQs etc) | 5
37 | Configuring the Jenkins | 5
38 | MongoDB table design | 3
39 | Design document preparation | 3
40 | Enabling Splunk | 5
Backlog | Master Data
41 | Master Data Preparation | 2
Backlog | API Test
42 | API Test Case Creation - Customer Service | 3
43 | API Test Case Creation - Order Service | 3
44 | API Test Case Creation - Inventory Service | 3
45 | API Test Case Creation - Mail Service | 3
46 | API Test Case Creation - BillingService | 3
47 | API Test Case Creation - EventService | 3

## OMS-Service-Priority
Service Name | Priority | Status
api-gateway | 1 | Done
product-service | 2 | Done
customer-service | 3 | Done
inventory-service | 4 | Done
oms-common-web | 5 | Done
oms-common-security | 6 | Done
oms-configurations-common | 7 | Done
event-service | 8
mail-service | 9 | Done
order-service | 10
payment-service | 11
billing-service | 12

## Tasks
Date | Ticket No | Tasks | Story Points | Owner | Status
25/9/2017 | OMS-0001 | Project creation, configuration, github code checkin for api-gateway | 1 | Panneer & Michael | Done
| OMS-0001 | Project creation, configuration, github code checkin for inventory-service | 1 | Panneer & Michael | Done
| OMS-0001 | Project creation, configuration, github code checkin for product-service | 1 | Panneer & Michael | Done
| OMS-0001 | Project creation, configuration, github code checkin for customer-service | 1 | Panneer & Michael | Done
| OMS-0001 | Project creation, configuration, github code checkin for order-service | 1 | Panneer & Michael | Done
| OMS-0001 | Project creation, configuration, github code checkin for event-service | 1 | Panneer & Michael | Done
| OMS-0001 | Project creation, configuration, github code checkin for payment-service | 1 | Panneer & Michael | Done
| OMS-0001 | Project creation, configuration, github code checkin for mail-service | 1 | Panneer & Michael | Done
| OMS-0001 | Project creation, configuration, github code checkin for billing-service | 1 | Panneer & Michael | Done
| OMS-0000 | github - Jenkins - PCF build deployment configuration for api-gateway | 1 | Ashok & Jagadeesan | Done
| OMS-0000 | github - Jenkins - PCF build deployment configuration for customer-service | 1 | Ashok & Jagadeesan | Done
| OMS-0000 | ER diagram changes & Collection fields updation | 1 | Sathish | Done
| Ticket No | Tasks | Story Points | Owner | Status
26/9/2017 | OMS-0002 | Add a customer to the repository | 3 | Panneer | Done
| OMS-0000 | Updating design documents with Instance, Messaging Details, Event Flow Diagram | 1 | Michael | Done
| OMS-0003 | Working on OMS-Common-Web | 2 | Ashok | Done
| Ticket No | Tasks | Story Points | Owner | Status
27/9/2017 | OMS-0003 | Search the customer based out of customer Id /name | 3 | Panneer &Ashok | Done
| OMS-0006 | Delete a customer based out of customerId | 2 | Panneer | Done
| OMS-0008 | Add a product into the repository | 3 | Michael | WIP
| OMS-0009 | Remove a product into the respository | 2 | Michael | Done
| OMS-0010 | View the product existence inside the repository | 1 | Michael | Done
| OMS-0011 | Search all the product based out of productId from the repository | 2 | Michael | Done
2017-03-10
| OMS-0013 | Add the product count,threshold to inventory by using productId | 2 | Rajsekar | Done
| OMS-0014 | Delete the product details to inventory by using productId | 2 | Rajsekar | Done
| OMS-0015 | Update product details to inventory by using productId | 2 | Rajsekar | Done
2017-04-10
| OMS-0005 | Modify the customer details based out of customerId | 3 | Panneer&Ashok | Done
| OMS-0008-11 | Addressed review comments for the task | 1 | Michael | Done
| OMS-0018 | Enable Swagger for all the endpoints. | 3 | Ashok | Done
| OMS-0012 | Search a product based out of name from the repository | 2 | Michael | Done
2017-05-10
| OMS-0007 | Display all the customers | 1 | Panneer | Done
| OMS-0019 | Implement API gateway for all the endpoints | 3 | Ashok | Done
| OMS-0013 | Update the product information in the repository. | 2 | Michael | Done
2017-06-10
| OMS-0014 | Groovy Configuration for "mail-service" | 1 | Rajsekar | Done
| OMS-0015 | Configuration of mail service | 1 | Rajsekar | Done
2017-09-10
| OMS-0021 | Project creation, configuration, github code checkin for oms-common-security | 1 | Panneer | Done
| OMS-0022 | Implementation of common security | 3 | Panneer | Done
2017-10-10
| OMS-0016 | Search an order based out of orderId | 1 | Ashok | Done | Without Unit Testing
| OMS-0017 | Create an Order with list of product items | 3 | Ashok | Done | Without Unit Testing
| OMS-0018 | Delete Order based out of orderId | 2 | Ashok | Done | Without Unit Testing
| OMS-0019 | Get the orders based out of customerId | 1 | Ashok&Panneer | Done | Without Unit Testing
| OMS-0020 | Get the order based out of customer Id and OrderId | 1 | Ashok&Panneer | Done | Without Unit Testing
|  | Lazy loading for "customer-service" | 1 | Michael | WIP
| OMS-0023 | Create an Invoice entry for every placed order | 2 | Panneer
| OMS-0024 | Send mail to the Customer | 2 | Panneer
| Task_Name | Customer Service | Story points | Owner | Status
| OMS-0004 | Viewing a customer, based out of customer Id | 2 | Panneer/Ashok
Inventory Service
| OMS-0016 | Search the product count for a productId | 2 | Rajsekar
Master Data
| OMS-0017 | Master Data Preparation | 2 | Jagadeesan/Sathish
Order Service
| OMS-0008 | Display all the orders based out of customerId | 1

## Task_Breakup details
S.No | Task Description | Story Points | Owner | Estimated Hrs | Actual Hrs | Remaining Hrs
DEV Team -
25/09/17 to 6/10/17
1 | Updating design documents with Instance, Messaging Details, Event Flow Diagram | 1 | Panneer & Michael | 8 | 8 | 0
2 | Project creation, configuration, github code checkin for api-gateway | 1 | Panneer & Michael | 8 | 8 | 0
Project creation, configuration, github code checkin for inventory-service
Project creation, configuration, github code checkin for product-service
Project creation, configuration, github code checkin for customer-service
Project creation, configuration, github code checkin for order-service
Project creation, configuration, github code checkin for event-service
Project creation, configuration, github code checkin for payment-service
Project creation, configuration, github code checkin for mail-service
Project creation, configuration, github code checkin for billing-service
3 | ER diagram changes & Collection fields updation | 1 | Sathish | 8 | 8 | 0
4 | Groovy Configuration - "customer-service" |  | Panneer & Ashok | 8 | 8 | 0
5 | Add a customer to the repository | 3 | Panneer | 8 | 8 | 0
| Coding |  |  |  | 4
| Unit Test Case |  |  |  | 4
6 | Search the customer based out of customer Id /name | 3 | Panneer & Ashok | 16 | 16 | 0
| Coding |  |  |  | 8
| Unit Test Case |  |  |  | 4
7 | Delete a customer based out of customerId | 2 | Panneer | 8
| Coding |  |  |  | 4
| Unit Test Case |  |  |  | 4
8 | Modify the customer details based out of customerId | 3 | Panneer & Ashok | 16
| Coding |  |  |  | 8
Unit Test Case
9 | Display all the customers | 1 | Panneer | 8 | 8 | 0
| Coding |  |  |  | 4
| Unit Test Case |  |  |  | 4
10 | Acceptance test case for CRUD Operations for "customer-service" |  |  |  | 4
11 | Groovy Configuration for "inventory-service" | 1 | Rajsekar | 4 | 4 | 0
12 | Add the product count,threshold to inventory by using productId | 2 | Rajsekar | 8
| Coding |  |  |  | 4 | 0
| Unit Test Case |  |  |  | 4 | 0
13 | Delete the product details to inventory by using productId | 2 | Rajsekar | 8
| Coding |  |  |  | 4 | 0
| Unit Test Case |  |  |  | 4 | 0
14 | Search the product count for a productId | 2 | Rajsekar | 8
| Coding |  |  |  | 4 | 0
| Unit Test Case |  |  |  | 4 | 0
15 | Update product details to inventory by using productId | 2 | Rajsekar | 8
| Coding |  |  |  | 4 | 0
| Unit Test Case |  |  |  | 4 | 0
16 | Acceptance test case for CRUD Operations for "inventory-service" |  |  |  | 4 | 0
17 | Groovy Configuration for "product-service" | 1 | Michael | 4 | 4 | 0
18 | Add a product into the repository | 3 | Michael | 8
| Coding |  |  |  | 6 | 0
| Unit Test Case |  |  |  | 2 | 0
19 | Remove a product into the respository | 2 | Michael | 8
| Coding |  |  |  | 6 | 0
| Unit Test Case |  |  |  | 2 | 0
20 | View the product existence inside the repository | 1 | Michael | 8
| Coding |  |  |  | 6 | 0
| Unit Test Case |  |  |  | 2 | 0
21 | Search all the product based out of productId from the repository | 2 | Michael | 8
| Coding |  |  |  | 6 | 0
| Unit Test Case |  |  |  | 2 | 0
22 | Addressed review comments for the task | 1 | Michael | 4 | 4 | 0
23 | Update the product information in the repository | 2 | Michael | 8
| Coding |  |  |  | 6 | 0
| Unit Test Case |  |  |  | 2 | 0
24 | Acceptance test case for CRUD Operations for "product-service" |  |  | 6 | 0 | 6
25 | "OMS-Common-Web" development and implementation | 2 | Ashok | 12 | 12 | 0
[5 empty] | 3 | 0
26 | oms-common-web service creation |  |  |  | 6 | 0
27 | Integration with other services |  |  |  | 3 | 0
28 | jenkins configuration |  | Ashok | 16 | 8 | 8
29 | Config server configuration | 2 | Ashok
30 | api-gateway development and implementation | 3 | Ashok | 12 | 12 | 0
31 | github - Jenkins - PCF build deployment configuration for api-gateway | 1
32 | github - Jenkins - PCF build deployment configuration for customer-service | 1
Mongo Team -
25/09/17 to 6/10/17 |  |  | Jagadeesan & Sathish | 8 | 8 | 0
33 | github - Jenkins - PCF build deployment configuration for product-service | 1 | Jagadeesan & Sathish
34 | github - Jenkins - PCF build deployment configuration for common-web | 1 | Jagadeesan & Sathish
35 | github - Jenkins - PCF build deployment configuration for inventory-service | 1 | Jagadeesan & Sathish
36 | Jenkins - HipChat configuration | 1 | Jagadeesan & Sathish
37 | Jenkins Automatic merge from "develop" to "master" | 1 | Jagadeesan & Sathish
38 | Developing queries with DEV team in needed places | 2
QA Team -
3/10/17 to 6/10/17
39 | Understanding OMS schema and microservices | 1 | Jagan & Bala | 8 | 8 | 0
40 | Environment setup | 1 | Jagan & Bala | 8 | 4 | 4
41 | Automation structure design for entire OMS Project | 1 | Jagan & Bala | 8 | 8 | 0
42 | "customer-service" endpoint - 1st Round of testing | 2 | Jagan & Bala | 16 | 8 | 8
DEV Team - Continues
43 | Groovy Configuration for "mail-service" | 1 | Rajsekar | 4 | 4 | 0
44 | Configuration of mail service | 2 | Rajsekar | 8
| Coding |  |  |  | 4 | 0
| Unit Test Case |  |  |  | 4 | 0
09/10/2017 -
DEV Team
| Project creation, configuration, github code checkin for oms-common-security | 1 | Panneer | 4 | 4 | 0
| Implementation of common security | 3 | Panneer | 16 | 4 | 8
| Unit Test and Acceptance test case for "product-service" |  | Micheal | 8 | 8 | 0
QA Team
| DS1 Sprint Activity |  | Jagan & Bala | 3 | 3 | 0
| V6 Training |  | Jagan & Bala | 1 | 1 | 0
| OMS - Sprint Activity - Inventory service |  | Jagan & Bala | 4 | 4 | 0
Mongo Team
10/10/2017 -
DEV Team
| Implementation of common security | 3 | Panneer | 16 | 12 | 0
| Search an order based out of orderId | 1 | Ashok | 2 | 2 | 0 | Without Unit Testing
| Create an Order with list of product items | 3 | Ashok | 6 | 6 | 0 | Without Unit Testing
| Delete Order based out of orderId | 2 | Ashok |  |  |  | Without Unit Testing
| Get the orders based out of customerId | 1 | Ashok&Panneer |  |  |  | Without Unit Testing
| Get the order based out of customer Id and OrderId | 1 | Ashok&Panneer |  |  |  | Without Unit Testing
| Lazy loading for "customer-service" | 1 | Michael | 8 | 8 | 0
QA Team
Mongo Team