## OMS Backlog
Order Management System Sprint Planning Document
Backlog | Customer Service | Story points | Priority
1 | Search the customer based out of customer Id /name | 1
2 | Add a customer to the repository | 3
3 | Viewing a customer based out of customer Id | 2
4 | Modify the customer details based out of customerId | 3
5 | Delete a customer based out of customerId | 2
6 | Display all the customers | 1
7 | Display all the orders based out of customerId | 1
Backlog | Order Service
8 | Search an order based out of orderId | 1
9 | Create an Order with list of product items | 3
10 | Delete Order based out of orderId | 2
11 | Get the orders based out of customerId | 1
12 | Get the order based out of customer Id and OrderId | 1
Backlog | ProductCatalog Service
14 | Add a product into the repository | 3
15 | Remove a product into the respository | 2
16 | View the product existence inside the repository | 1
17 | Search a product based out of productId from the repository | 2
18 | Search a product based out of name from the repository | 2
19 | Update the product information in the repository. | 2
Backlog | Inventory Service
20 | Add the product count,threshold to inventory by using productId | 2
21 | Delete the product details to inventory by using productId | 2
22 | Update product details to inventory by using productId | 2
23 | Search the product count for a productId | 2
Backlog | Mail Service
24 | Send a confirmation mail after the order is placed | 2
25 | Send an Invoice mail if the customer requests for the specific order | 2
Backlog | Cross Cutting Concerns
26 | Implement API gateway for all the endpoints | 5
27 | Inject security for all the endpoints | 5
28 | Enable Swagger for all the endpoints. | 3
29 | Logging specific to OMS system | 3
Backlog | BillingService
30 | Create an Invoice entry for every placed order | 2
31 | Send mail to the Customer | 2
Backlog | EventService
32 | Create an event for every order creation, order status updation | 5
33 | Fetch the events based out of orderId | 3
34 | Fetch all the events based out of statuses | 3
35 | Fetch all the events based out of eventName | 3
Backlog | Others
36 | Configuring the Pivotal Environment(like configuring RabbitMQs etc) | 5
37 | Configuring the Jenkins | 5
38 | MongoDB table design | 3
39 | Design document preparation | 3
40 | Enabling Splunk | 5
Backlog | Master Data
41 | Master Data Preparation | 2
Backlog | API Test
42 | API Test Case Creation - Customer Service | 3
43 | API Test Case Creation - Order Service | 3
44 | API Test Case Creation - Inventory Service | 3
45 | API Test Case Creation - Mail Service | 3
46 | API Test Case Creation - BillingService | 3
47 | API Test Case Creation - EventService | 3

## OMS-Service-Priority
Service Name | Priority | Status
api-gateway | 1
product-service | 2
customer-service | 3
inventory-service | 4
oms-common-web | 5
oms-common-security | 6
oms-configurations-common | 7
event-service | 8
mail-service | 9
order-service | 10
payment-service | 11
billing-service | 12

## Sprint 1
Date | Tasks | Story Points | Owner | Status
25/9/2017 | Project creation, configuration, github code checkin for api-gateway | 1 | Panneer & Michael | Done
| Project creation, configuration, github code checkin for inventory-service | 1 | Panneer & Michael | Done
| Project creation, configuration, github code checkin for product-service | 1 | Panneer & Michael | Done
| Project creation, configuration, github code checkin for customer-service | 1 | Panneer & Michael | Done
| Project creation, configuration, github code checkin for order-service | 1 | Panneer & Michael | Done
| Project creation, configuration, github code checkin for event-service | 1 | Panneer & Michael | Done
| Project creation, configuration, github code checkin for payment-service | 1 | Panneer & Michael | Done
| Project creation, configuration, github code checkin for mail-service | 1 | Panneer & Michael | Done
| Project creation, configuration, github code checkin for billing-service | 1 | Panneer & Michael | Done
| github - Jenkins - PCF build deployment configuration for api-gateway | 1 | Ashok & Jagadeesan | Done
| github - Jenkins - PCF build deployment configuration for customer-service | 1 | Ashok & Jagadeesan | Done
| ER diagram changes & Collection fields updation | 1 | Sathish | Done
26/9/2017 | Tasks | Story Points | Owner | Status
| Add a customer to the repository | 3 | Panneer | Done | OMS-0002
| Updating design documents with Instance, Messaging Details, Event Flow Diagram | 1 | Michael | Done
| Working on OMS-Common-Web | 2 | Ashok | WIP
| Customer Service | Story points | Owner | Status | Task_Name
| Search the customer based out of customer Id /name | 1 | Panneer/Ashok
| Viewing a customer based out of customer Id | 2 | Panneer/Ashok
| Modify the customer details based out of customerId | 3 | Panneer/Ashok
| Delete a customer based out of customerId | 2 | Panneer/Ashok
| Display all the customers | 1 | Panneer/Ashok
| Display all the orders based out of customerId | 1 | Panneer/Ashok
ProductCatalog Service
| Add a product into the repository | 3 | Michael/Ganesh
| Remove a product into the respository | 2 | Michael/Ganesh
| View the product existence inside the repository | 1 | Michael/Ganesh
| Search a product based out of productId from the repository | 2 | Michael/Ganesh
| Search a product based out of name from the repository | 2 | Michael/Ganesh
| Update the product information in the repository. | 2 | Michael/Ganesh
Inventory Service
| Add the product count,threshold to inventory by using productId | 2 | Rajsekar
| Delete the product details to inventory by using productId | 2 | Rajsekar
| Update product details to inventory by using productId | 2 | Rajsekar
| Search the product count for a productId | 2 | Rajsekar
Master Data
| Master Data Preparation | 2 | Jagadeesan/Sathish